## UAT Test Cases
Test ID | Jira ID | Requirement ID | Test Scenario | Preconditions | Test Steps | Expected Result | Actual Result | Status | Tester
UAT-01 | SCSI-8 | FR-01, FR-02 | Validate mandatory service-request information | Service request form is available | Create a request and leave mandatory customer/equipment/issue information incomplete; submit/continue | Missing mandatory information is identified and the request cannot proceed normally until completed | Mandatory information validation works as expected | Passed | Key User
UAT-02 | SCSI-9 | FR-05 | Validate standardized case routing | Approved routing rules are configured for test | Create a case with a category mapped to a specific service team; execute routing | Case is assigned to the correct responsible team according to the approved routing rule | Case routed to expected team | Passed | Key User
UAT-03 | SCSI-10 | FR-08 | Validate remote vs Field Service decision | Test case requiring physical on-site work is available | Perform remote assessment; record that on-site activity is required | Case proceeds to the Field Service path | Field Service path triggered correctly | Passed | Customer Service Key User
UAT-04 | SCSI-11 | FR-09, FR-10 | Validate Field Service handover readiness | Case requiring Field Service exists | Prepare handover with one mandatory Field Service field missing; attempt to proceed | Request does not proceed to normal technician planning until mandatory information is completed | Incomplete handover correctly identified | Passed | Field Service Key User
UAT-05 | SCSI-12 | FR-12, FR-13 | Validate Field Service status/result visibility | Field Service activity linked to a service case exists | Update Field Service activity status and record service result; review originating case | Relevant Field Service status and result are available to Customer Service | Status and result visible as expected | Passed | Customer Service Key User
UAT-06 | SCSI-13 | FR-15 | Validate standardized case closure | Resolved case with incomplete mandatory resolution information exists | Attempt to close case; complete required resolution information; attempt closure again | Initial closure is prevented; after required information is completed, case can be closed | Closure validation works as expected | Passed | Key User